## Sheet1
know.area | stage |  | frequency | report | duration | 1st | 2nd | input | Details | [7 empty] | Output
Study Schedule
|  |  |  | scope | time |  |  | cost | quality | hr | communi | risk | procurement | integration | stakehol | codeofeth | exam out | app concp | exam
|  | 1 | 3 | 5 | 6 |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 4 | 13 | 14
[8 empty] | 12: NOV11-17; 4: NO18-24 |  |  | 2013-12-07
PMP, Rita | bar: 12 to 14
PMBOK | Pmbok | bar: 7 to 10; 12 to 14
Visio-Chart | [7 empty] | 7: 50%; 8: 50%; 11: vid
Visio-PMP processes | bar: 7 to 10; 12 to 14
Rita, Ques |  | ? | ?
Rita, Prob |  | ? | ?
| decip PMBok | [6 empty] | Earned Value: A Brief Overview |  |  | Communication Management Exam Tips | Seinfeld: The Risk Management Episode | Procurement Tips | Types of Exam Questions | PMI Code of Ethics and Professional Responsibility
Bonus Study Game - Role of the Project Manager
Answer Key - Role of the Project Manager Game
Video | [7 empty] | 13: Some Tips Before You Go
|  |  | 30 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 31 | 1 | 1 | bar: 7 to 12
|  |  | 32 | 2.1 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2
|  |  | 33 | 2.2 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 34 | 3 | 4 |  |  | 7: 4; 8: 4; 9: 4; 11: 4; 12: 4
|  |  | 35 | 4 | 5 |  |  | 7: 5; 9: 5; 11: 5
|  |  |  | 5.1 | 6 |  |  | 9: 6; 11: 6
|  |  |  | 5.2 | 7 |  |  | 11: 7 | add gaps
|  |  |  | 6 | 8
Assesment | [7 empty] | 11: 65% | add gaps
Quiz ranking
Assignment | [7 empty] | 9: hr theories; 11: Discussion - The Greatest Risk; 12: Write your own Exam Question; 4: The Project Charter; 13: What's Next for You?
[10 empty] | brain dump |  | Risk Self-Assessment |  | Challenging Integration Management Practice Exam Questions | Final Exam
Integration Vocabulary Match Exercise
Project Integration Vocabulary Match
(optional) |  |  |  |  | OPTIONAL Additional Critical Path Exercises |  |  | 4: Project Integration Practice Exam Results
review feedback
Exam content guide
Exam | [7 empty] | 11: 1; 12: 2; 4: 3; 13: 4; 14: prep | checked | flashcards | braindump
1 | 70% | 78% |  | 83.33% | 50% |  |  | 33.33% | 53.85% | 66.67% | 66.67% | 75% | 92.31% | 66.67% | 71.43% |  | add gaps
2
3
4
5
6
7
8
9
10
HR chart
Sponsor Chart
PM Chart
practice brain dump
flash cards
Brain Dump |  |  | - Table 3-1 of the PMBOK® Guide 4 |  |  |  |  | 12: problems got wrong | hard problems
|  |  | th |  |  |  |  | 12: (flash cards)
Edition
- Formulas, such as earned value, PERT, communication channels, procurement,
probability, project selection and depreciation
- Values, such as 1, 2 and 3 sigma and estimate ranges
- Acronyms, such as BAC or TCPI
- Powers of a project manager
- Conflict resolution (best to worst)
- Sources of Conflict (order of priority)
- Herzberg’s motivators
- project closing check list
And of course: you must include all the items that you personally have trouble
remembering during your studies and that you feel need to go onto your sheet. The list
above or using a Brain Dump that someone else created can be a good start but you
really need to customize it to your needs. Don’t study what others are having trouble
remembering. Instead, include what gives you the hiccups.
Exam day |  |  | Relax
Executive dashboard
Sponsor dashboard
PM dashboard
project report
Report heirachy
Executrive
Sponsor
PM
Project team
Area | Stage |  | Frequency | Report | Dur |  |  | 7: INPUTS; 8: DESCRIPTION (TOOLS & TECHNIQUES) | OUTPUT | Next (Project)
|  | Project Management |  |  |  | PM |  | 8: Expert at project management
[6 empty] | PM |  | 8: staying ahead of the project
|  | PMO | [5 empty] | 8: department to manage projects
|  | Stakeholders |  |  |  | TM | PM | 8: technical experts
Integration | initiating | Develop Project Charter | [5 empty] | 8: High-level objectives, constraints, requirements, scope, risks, and assumptions; Assess whether feasible within given constraints
Tools: Expert Judgement, Facilitation techniques
Sponsor
Agreements
[8 empty] | Business case | market demand, organizational need, customer request, technological advance, legal requirement, ecological impacts, social need
[8 empty] | Statement of work | Business need, product scope description, strategic plan
[8 empty] | EEA | (other)
[8 empty] | OPA | (Process and procedures, knowledge-base)
[8 empty] | 8: Title and description |  | Kitchen re-model BPI-web app (stakeholders), project team, project documents
What
Problem description
Purpose:"investigate reasons for problem and propose a solutions"
"Solution authorized as a subsequent project"
Source of data
[8 empty] | 8: manager assigned and authority level; 12: who, can he/she determine, manage, and approve changes to bdget, schd. Staffing, etc. |  | requires approval from sponsor.
[8 empty] | 8: business case |  | Need to position for possible sale
[10 empty] | need |  |  | why is project being done
slection committee
financial or other justification "we expect…
purpose
justification
othe benefits
[10 empty] | selection methods |  | benefit measurement methods (Comparative)
Murder board/shoot-down project
Peer review
Scoring models
Economic models
constrained optimization
Linear programming
[10 empty] | fit |  |  | Integer programming
Dynamic programming
Multi-objective programming
[8 empty] | 8: resources Preassigned |  | Owner, General contractor and vendors
how many or which resources will be provided
[8 empty] | 8: Stakeholders; 12: who will be affected by the project |  | Owner, prospective buyer
[8 empty] | 8: Stakeholder requirements as Known |  | - Keep mep in place - cost no more than $10k - energy efficiency - granite / marble countertops - resurface cabinets
utilizing the data
regulatory requirements, benefits, confidnetiality, security
[8 empty] | 8: Product Description/Deliverables |  | - New energy saving appliances - New fixtures - New countertops - New cabinets surfaces -manage inernal temp.(interior and exterior sensors) -maintain uses of related items (bright light for prepare food,.. -fix issues (dishwashing, --> -have heat and fresh air at the same time - big pot wash -recyclables -newspaper disposal - recycling |  |  |  | -soak water, scrub with soap, into rinse water, oak water into toilet, shower rinse, air dry, remove tray. -open windows, turn on extractor fan, cover -generate alternates (ask around)
report on: what, cost, result of change; few words; agreed to by data source, customers and marketing, and team
list of interactions with customers
WBS when
list of risks when
[8 empty] | 8: Assumptions |  | - Buy all materials locally - Work will cost less than - Buy all materials locally - Work will cost less than $10k
(believe to be true; believe to be the case, but no data)
requirements, integration, resources, available expertise, available time
[6 empty] | kjl; |  | 8: Contraints |  | - Work completed in two weeks - Power requirements, water pressure constraints
factors limiting ability to deliver,boundaries or parameters
wbs completed in wks
Risk register due in wks
The scope is only to:
[8 empty] | 8: Measureable project objectives; 12: due no later than, budget |  | Budget: $10k Delivery: 2weeks (whole kitchen)
[8 empty] | 8: project approval requirements; 12: WBS, list of risks, final project approval |  | - Materials have to be approved before purchase by General contractor. - Countertop and cabinet drawings reviewed before fabrication.
[8 empty] | 8: high level project risks; 12: opportunities and risks |  | General Contractors - Qualified - Honest, experienced
sponsors authorizations
Project Charter
[18 empty] | Develop Project Management plan | 4.2
[18 empty] | Plan scope management | 5.1
[18 empty] | Collect Requirements | 5.2
[18 empty] | Define scope | 5.3
[18 empty] | plan schedule management | 6.1
[18 empty] | plan cost management | 7.1
[18 empty] | plan risk management | 11.1
[18 empty] | identify stakeholders | 13.1
Integration | Planning | Develop Project Management Plan |  |  |  | PM
Project baselines include:
|  |  |  | table-web | [12 empty] | Scope baseline | kitchen remodel
|  |  |  | table-web | [12 empty] | Schedule baseline | 2 weeks
|  |  |  | table-web | [12 empty] | Cost baseline | 10k
Subsidiary plans:
|  |  |  | table-web |  |  |  | 12: 5.5.3.1 | Scope management plan
|  |  |  | table-web |  |  |  | 12: 5.1.3.2 | Requirements management plan
|  |  |  | table-web |  |  |  | 12: 6.1.3.1 | Schedule managementplan
|  |  |  | table-web |  |  |  | 12: 7.1.3.1 | Cost management plan
|  |  |  | table-web |  |  |  | 12: 8.1.3.1 | Quality management plan
|  |  |  | table-web |  |  |  | 12: 8.1.3.2 | Process improvmenet plan
|  |  |  | table-web |  |  |  | 12: 9.1.3.1 | Human resource management plan
|  |  |  | table-web |  |  |  | 12: 10.1.3.1 | Communications management plan
|  |  |  | table-web |  |  |  | 12: 11.1.3.1 | Risk management plan
|  |  |  | table-web |  |  |  | 12: 12.1.3.1 | Procurement management plan
|  |  |  | table-web |  |  |  | 12: 13.2.3.1 | Stakeholder management plan
may include:
life-cycle selected for the project and process
details of the tailoring decisions specified by the PM Team
|  |  |  | ? | [13 empty] | processes
|  |  |  | ? | [13 empty] | level of detail
|  |  |  | ? | [13 empty] | tools & techniques
|  |  |  | ? | [13 empty] | process input/ouput descriptions
description of how work will be executed to accomplish the project objectives
chagne management plan that documents how changes will be moniotred and controlled
configuration management plan that documents how configuration management will be performed
description of how the integrity of the project baselines will be maintaines
requirements and techniques for communicating
key mangaement reviews and timing to open and adress open issues and pending decisions
[18 empty] | Direct and manage project work | 4.3
[18 empty] | Monitor and control project work | 4.4
[18 empty] | Perform integrated change control | 4.5
[18 empty] | Close Project or Phase | 4.6
Integration | Executing | Direct and Manage Project Work |  |  |  | PM |  | 8: put all pieces together into a cohesive whole
[8 empty] | 8: Tools: Expert Judgement, Project Management Info System, Meetings | KPIs
|  |  |  | dashboard | daily | Team | PM | 8: performa activies to accomplish project objectives
|  |  |  | dashboard | daily | Team | PM | 8: Create project deliverables to meet the planned project work |  | Specifications Shop Drawings Reskinned Cabinets Installed new doors Installed new countertop Replaced Kitchen Sink Cabinet New Sink New Dishwasher, ES New Double Oven, ES Lighting, Adjs ES Adjust Blinds, Room thermostat Linux Rasberry w/Python Server w/wifi Server mount EE Windows Wall mount A/C Solar Panels Security system rumba cabinet park recessed mat area
|  |  |  | dashboard | as required | PM |  | 8: Provide, train and manage the team members assigned to the project | Project management plan updates | BIM, db BOM
[5 empty] | as required | PM | Team | 8: Obtain, manage and use resources including materials, tools, equipemtn and facilities |  | Countertops, Appliances, EE parts
|  |  |  | audit |  | Team |  | 8: implement the planned methods and standaerds
|  |  |  | monitor | daily | PM |  | 8: Establish and mangemen project commication channels, both exteranl and interal to the project team | Project management plan updates | project status e-mails
|  |  |  | dashboard | as required | PM |  | 8: Issue change requests and impelent approved chagnes inot the prject's scope, plans, and environment |  | change db
|  |  |  | monitor | daily | PM | Team | 8: manage risks and implement risk response activities | Project management plan updates | risk management register
|  |  |  | monitor | as required | Team | PM | 8: manage sellers and suppliers
|  |  |  | monitor | as required | PM |  | 8: manage stakholders and their engagement; and |  | stakeholder register
|  |  |  | database | as required | Team | PM | 8: collect and document lessons learned and implement approved process improvement activiteis | Project management plan updates | ll db
|  |  |  | dashboard | daily | PM |  | 8: Review impact of changes
|  |  |  | database |  |  |  | 8: - Project Scope updates |  | change db
|  |  |  | database |  |  |  | 8: - Internal PM Change-Corrective Action, Preventative Action, Defective Repair |  | change db
|  |  |  | dashboard | daily | PM | Team | 8: Approved change requests
|  |  |  | monitor | daily | Team | PM | 8: Implementation of changes | Change requests | Perform Integrated Change Control | 4.5
|  |  |  | dashboard | daily | [11 empty] | Deliverables | Control Quality | 8.3
|  |  |  | dashboard | daily | [11 empty] | Work performance data | Validate scope | 5.5
|  |  |  | dashboard | daily | [11 empty] | Work performance data | Control scope | 5.6
|  |  |  | dashboard | daily | [11 empty] | Work performance data | Control schedule | 6.7
|  |  |  | dashboard | daily | [11 empty] | Work performance data | Control Costs | 7.4
[17 empty] | Work performance data | Control COMmunications | 10.3
[17 empty] | Work performance data | Control Risks | 11.6
[17 empty] | Work performance data | Control Stakeholder Engagement | 13.4
Integration | Monitoring | Monitor and Contorl Project Work |  |  |  | PM |  | 8: Tracking, review and reporting progress
[8 empty] | 7: Work performance Information |  | Web dashboard ASP.net
[8 empty] | 7: Schedule Forecasts; 12: ETC, SV, SPI |  | Web dashboard ASP.net
[8 empty] | 7: Cost Forecasts; 12: ETC, CV, EAC, BAC, CPI |  | Web dashboard ASP.net
[8 empty] | 7: Validation chagnes |  | Web dashboard ASP.net
OPA, EEF
[17 empty] | Change Requests | Perform integrated change control | 4.5
[17 empty] | Work Performance Reports | Manage Project Team | 9.4
[18 empty] | Manage Communications | 10.2
[18 empty] | Control Risks | 11.6
[18 empty] | Control Procurements | 12.3
Integration | Monitoring | Perform Integrated Change Control | [5 empty] | 8: Evaluate impact of chagnes elsewhere
Tools & Tech: Expert Judgement, Meetings, Change Control Tools
[6 empty] | 90 |  | 7: Change Requests; 9: 5.5-13.4
Evaluate impact, id options, get approved, get buy-in
[8 empty] | 7: (Change Control Board) |  | change db
[17 empty] | Project document updates | change log
|  |  |  | database | [12 empty] | Approved Change requests | Control Quality | 8.3
[17 empty] | Approved Change requests | Control Procurements | 12.3
[17 empty] | Change log | Manage Stakeholder Engagement | 13.3
Integration | Closing | Close Project or Phase
Tools & Techniques: Regression analysis, and Trend analysis
Project Management plan
Accepted deliverables
[8 empty] | OPA | Project closure guidelines, lessons learned db
Final Product
[17 empty] | OPA updates | opa database
Stakeholder | Initiating | Identify Stakeholders | initial, continual |  |  |  |  | 8: Tools:Stakholder analysis, expert judgement, meetings | [5 empty] | Impact
Project Charter
[8 empty] | procurement documents |  |  | Suppliers, Subcontractors, agreements, laws
EPA, EEF
[8 empty] | 8: Analyze potential Impact | Stakeholder Register
[8 empty] | 8: Identify all | id | name | Title | Dept/super | Contact infor | requirements |  | expectations | interest | level of influence | how to manage | how comm. | manage exp | comm-freq. | control stk comm & engage
[18 empty] | Prospective buyers |  |  |  | TBD |  | want to buy
[18 empty] | Owner |  |  |  | EE, water conserv., able to sell, manage washing Dishes, hot/cold, smoke from cooking, broken screen, manage recycling, storage ease, high-spoil items, shopping list, life |  | life-time expectations
[18 empty] | GC |  |  |  | 4% |  | 4%
[18 empty] | Subcontractors |  |  |  | time and materials -fixed |  | paid on time
[18 empty] | Supplies |  |  |  | fair price |  | no returns
[18 empty] | Guests |  |  |  | sun shade |  | comfortable
Determine their requirements
[9 empty] | Deterine their expecations |  |  | what will happen as a result
Determine their interest
Determine their level of influence
Plan how to manage them
Plan how you will communicate with themmanage their expectations, influence and engagement
Communicate with them
Control communications and stakeholder engagement
[8 empty] | 8: Classification Models |  | Chart-Salience model
Power/interest grid-level of authority and concern (low, mid, high)
[8 empty] | 8: (monitor, keep satisfied, manage closely, keep informed) |  | Chart
Power/influence grid - ..and active involvement
Influence/impact grid- .. Ability to effect changes
|  | Flash card | [5 empty] | 8: Salience model - ability to impose will , urgency, legitimacy
weekly-log any new comittments, give/take
Stakeholder | Planning | Plan Stakeholder Management | [5 empty] | 8: Tools: Expert Judgement, Meetings, Analytics techniques
[8 empty] | project management plan | life cycle, description of work, how hr will be met,
Stakeholder register
EPA, EEF
[6 empty] | PM |  | 8: Close you are to stakeholders, the more comfortable they are coming to you with problems
[6 empty] | PM |  | 8: Spend time with stakeholders
[6 empty] | PMT |  | 8: Characteristics of a good relationship
Trust
Honesty
Good communications
Interest
Sincerity
Respect
Concern
Sympathy
[9 empty] | Analytical Techniques |  |  | Stakeholder, unaware, resident, etc.. "C"=current , "D"=Desired
Unaware
Resistant
Neutral
Supportive
Leading
[6 empty] | PM |  | 8: Examples
[6 empty] | PM |  | 8: Invite to participate in risk management process |  | review and add to register
[6 empty] | PM |  | 8: send reports |  | email, weekly one page
[6 empty] | PM |  | 8: get stakeholder apporval |  | set review milestones, decentralize
[6 empty] | PM |  | 8: root cause-non-support |  | meetings
[6 empty] | PM |  | 8: invite stakholders to officially join pm team |  | email
[6 empty] | PM |  | 8: plan to meet periodically |  | daily-dinner
[6 empty] | PM |  | 8: forward literature and training to help stakeholder |  | solicit - by special e-mail, forward email
|  |  |  | submit to sponsor for review |  |  |  | 8: not include too sensitive information | Stakeholder management plan
[18 empty] | Collect requirements | 5.2
[18 empty] | Manage Stakholder Engagement | 13.3
Stakeholder | Executing | Manage Stakeholder Engagement
[8 empty] | 7: Stakeholder management plan | documentation of lessons learned
[8 empty] | 7: communications management plan | change requests
[8 empty] | 7: change log | recommended corrective and preventative actions
[8 empty] | 7: OPA | issue log updates
project manageent plan updates
Stakeholder | Monitoring & Contorlling | Control Stakholder Engagement | [5 empty] | 8: Tools:
Communication methods
Interpersonal Skills (build trust, resolving conflict, active listening, overcoming resisitance to change)
Management skills - facilitate, influence, negotiate, modify oganizational behaviour
Stakeholder management plan
Communications management plan
Change log
OPA- issue management procedures, change control proceudres, historical process info.
Perceptions of project process
look for variances
talking, listening and gathering information
Ask open ended questions
draw on expertise of others
look for patterns and make necessary adjustments
[17 empty] | Work performance information | Monitor and control project work | 4.4
[17 empty] | change requets | Perform integrated change control | 4.5
OPA
Scope | planning | plan scope management | [5 empty] | 8: Methods used to plan, execute, monitored, controlled and verfied processes
How to achieve scope
How to create WBS (CSI, Architecture-decompose)
How to manage and control (change control) – Oracle Exp., Configuration, Source control software
How to obtain acceptance – milestones, payment
What tools – PLM, Scheduling, Excel..
Enterprise Environmental Factors – Government regulations, trend, culture
Operational Procedural Assets – Templates, project files, historical, policies, procedures, lessons learned
Project Charter, SOW (High-level description, purpose, justification, characteristics, results, project approval requirements, measureable objectives, success critieria, major risks, major, milestones, budget, list of stakeholders, sponsors, project manager)
Requirements Management Plan (O) – method to define and document stakeholder needs
(prioritize, configure, report, manage, metrics/analyze)
Scope | planning | collect requirements | [5 empty] | 8: Methods for Collection – Business and Stakeholder needs (data and analysis, prototypes, benchmarking)
Collect explicit and implicit and explicit needs
Organize into categories (business, stakeholder, solution-features, functional, non-functional, transition (temp conditions eg. Test lab, project, quality)
Provide enough detail
Decision making: unanimity, majority, plurality, dictatorship
stakeholder register-Identify Stakeholders and determine their expectations, communication requirements, influence and impact
(beliefs, mental pictures 9+ RM Pg 164)
Stakeholder Management Plan (O) (Methods to define and document needs eg. group, type, level of buy-in, influence (H/M/L), strategies to deal with resistance, person)
charter
[7 empty] | Quickest | 8: Survey
[7 empty] | Ranking | 8: Nominal group technique - rank ideas from brainstroming
multi-criteria dec. analysis - rank (risk, time, cost, benefit)
Affinity digrams - ideas grouped by similarities
context diagrams - scope w/integates to people, process and systems
delphi - experts, anonomous, RFI
Group decision making: unaminity, majority, pluarity (largest group), dictatorship
[6 empty] | (Include requirements not included) | [10 empty] | Requirements documentation
– business, stakeholder, transition, quality, training, business solutions, assumptions, impacts,
business support, constraints, acceptance criteria
- measurable, testable, traceable, consistent and acceptable
Requirements tracability matrix
Requirements Traceability Matrix (O) : i. Requirements (y) x features (x) ii. Req. (y) x Test case (x)
-Life of requirement,
-link to business objectives, track changes
Project Deliverables, Product Design and Development, Product Test approach
[6 empty] | ID | AssID | Req. Descrip | Business need, Opp, goals, objectives |  | project objecti | WBS deliverable | product design | product desictipoin | test cases |  | Validaion req., test cases
Scope | planning | define scope | baseline |  |  |  |  | 8: T&TExpert Judgement (SME’s, stakeholders, consultants, industry),
Product Analysis (Systems Engr, Value Engr.),
Alternatives Generation, Facilitated Workshops -lead to common understanding and limits
Project Risks, Assumptions and Constraints
Scope management plan
Charter
Project Scope Statement (O)
|  |  | need precise language |  |  | - “Here is what we will do on the this project”
-“Here is the entire approved project and product scope for this project”
- Deliverables
- Acceptance Criteria
- what is not part of the project
- Additional risks, assumptions and constraints
- Key project reporting points – milestone, design reviews, weekly, etc.
Project Document Updates (O)
- Stakeholder register, Requirements documentation, Req. traceability matrix
Scope | planning | create wbs | [5 empty] | 8: Decomposition, Expert Judgement
- scope Management Plan
- project scope Statement
- Requirements Documentation
- Enterprise Environmental Factors
- Organizational Process Assets
-Control Accounts (allows for aggregation and analysis of work perform. data regard. costs, sched. &scope)
Control account=management conrol point, where scope, budget, cost and schedule are integrated
|  |  | Level of effort activity=support-type |  |  |  |  | 8: -Work Packages (8 hrs min., can be scheduled, budgeted, assigned and are necessary and sufficient.)
second level=phases or major deliverables
-WBS Dictionary (Code of Account ID#, WP#, Person, Date, Description, Deliverable, work, acceptance criteria, assumptions, constriants, quality metrics, tech source. Doc, risks, resources, duration, scd. Milestones, cost, due date, interdep. Act. App/PM
(eg. CSI Code, user, stories, use cases, features, source control specification)
Scope Baseline
Project scope statement -description of project scope, deliverables, assumptions
meaningful conclusion, end of log. subdiv., realistically estimated
WBS
[6 empty] | PT | Approved by PM | [9 empty] | WBS Dictionary | (# allows id of indiv. Items) | code of acct | desc of work | assumptions/constratints | responsible org | schedule milestones | associate sch. Act | resources req. | cost est | quality req | accept criteria | tech refer | agree inform.
Time | planning | plan schedule management | [5 empty] | 8: how will scheduled be planned, managed and controled (list)
SME’s, Expert Judgement, Analytical Tools
Who will be involved
What approach /method and tools eg. CPM, p6
Processeses and Procedures – sched. Template
Enterprise Environmental Factors – est. past projects, work auth. Process
How to measure and when?
Units of measure for work and duration (hrs, days)
Acceptable variances
How to ID variances
Reporting formats (Earned value, how often, sch. Details, overview)
Schedule Management Plan (O)
Time | planning | define activities | [5 empty] | 8: Decompose WBS into activities and sequence
plan scope outputs, id risks
Organization Process Assets (Templates, Hist. Info, Act.lists, Standards)
Rolling-wave planning - plan to higher level, wait until work is clearer to plan at lower levels
Milestones-significant events
Time | planning | sequence activities | [5 empty] | 8: Work Flow + ID Opportunities to compress + options to the schedule, ID relationships
Activity list
activity attributes-realtions
milestone list
scope statement
eef
smp
[8 empty] | 7: opa | Network Diagram (O)
[9 empty] | Methods | FS, SS, FF, SF
[8 empty] | 8: GERT – Graphical Evaluation and Review Technique | Allows loops
[9 empty] | Dependency |  | Project Team - Mandatory, pref/ discret; PM – Ext/Int
Time | planning | estimate activity resources | [5 empty] | 8: Type and Quantity incl. equipment and materials, analyze,reserves, non-working /working calender. Milestones, review risk register
[6 empty] | by person doing the work | PM-provide the information | 8: smaller work packages, more accurate; realistic
people, equipemnt and materials
anlaysis of reserves needed on project - contingency and management reserves (additional funds)
review risk register for additional information
"padding"-management errors
sanity check estimates
record assumptions for review later
Activity Resource Requirements (O)
Resource Breakdown Structure (O)
Time | Planning e | estimate activity durations | [5 empty] | 8: Confidence +/-, sanity check, establish researves /contingencies, est. method to better control projects
|  |  | Periodically perform estimate complete |  |  |  |  | 8: Estimating Methods
One-point estimating - one estimate per activity
[8 empty] | most costly | botti=om up
[8 empty] | (Top-down) | Analogous (Top-down) - historical to predict future
[8 empty] | rate | Parametric - look at relationships in data to estimate (a-regression analysis (scatter diagram, learning curve)
Three-point estimating - optimistic, pessimitic, most likely
Expanded activity -Triangular (simple average) = P+O+M/3
Expanded Activity - Beta dist. /PERT (weighted average) = P+4M+O/6
Beta activity standard deviation = P-O/6
Time | planning | develop schedule | [5 empty] | 8: calender-based, apporved and realistic
historical records
resource calender
risk register
understanding of the work, , activity list and attributes, order-network diagram, durations, resource req., resource list,
look for alternative ways to complete and opportunities
have team approve final schedule, have meetings for buy-in
test by compressing schedule, crashing, fast-tracking, and reestimating
Schedule network analysis
CPM-longest path
[6 empty] | PM |  | 8: day-to-day management with Network Diagram / PrecedenceDiagramming Method (PDM)
- Near-Critical path – the Near-Critical path becomes Critical if the Critical path is shortened.
schedule compression:
fast-track: doing series work in parallel
[8 empty] | 9: crashing: add or adjust resources | increase cost
Modeling-simulate using monte carlo analysis- prob completeing on a day, for a specific cost, or any activity on critical path, overall project risk
resource optimization
Resource Leveling – lengthens sch., Incr. cost
resource smooting -leveled withing limits of the float of actiityes
Critical Chain method - assign each activity to occur as late as possible with CPM, ND
|  |  |  | Stakeholder approvals | [12 empty] | Project Schedule (O)
|  |  |  | management | [12 empty] | Mileston chart - milestone by month with diamonds and dates
bar charts - activity, duration, s,f, by week, with diamonds and bards
Cost | planning | plan cost management | [5 empty] | 8: how will be managed (see list)
funded with equity or debt; purchase / lease
analytical techniques: IRR, NPV, payback period
Cost | planning | estimate costs | [5 empty] | 8: quality, risk, pm, activities, direct (labor, materials, training, computers), office, profit, OH
on-point, analoaguosu (hist.), parametric, 3point-est, bottom up
Deter. Resource cost rates
consider O&M costs
Accuracy: ROM (-25 to +75%), Budget (-10-+25%), Definitive (+/-10%)
Deter Budget: Act Est->Work pack est->CA es->Proj est.+Cont. Est->cost bas.-> Manag. Reservers=Cost budget
Do sanity check and compare with histroical , parmetric, expert judgement
Justify significant differences
Do funding limit reconciliation/check cash flow
one-time phased spending plan
Cost | planning | determine budget
Quality | planning | plan quality management | [5 empty] | 7: Customer definition of quality
Stakeholder register
degree to which project fullfills requirements
|  |  |  | Objective -no expert judgement |  |  |  | 8: Theorists
80/20 principle - Joseph Juran
14 points of TQM- W. Edwards Deming
"zero defects" Philip Crosby
|  |  |  | Range - tolerance |  |  |  | 8: , determine meterics,
|  |  |  | Hig precision instruments have little scatter |  |  |  | 8: plan for continuall process improvement
quality standards and processes that are papplicabel to the project
metrics to measure quality from the customer's and org perspective
test the validity of assumptions, before result in problems
collect issues, and implement corrective action
perform quality reviews
reasses quality standards
[5 empty] | eg. ISO 9000, OSHA |  |  | 8: Plan Quality management - define quality (appropriate to needs of project), and work to meet standards
Quality Assurance - ensure participation, quality audit, assess quality measurements
[5 empty] | Threshold=control limits |  |  | 8: Control Quality-examines deliverables
7 Quality Tools:
Cause and effect-Fishbone, to find root cause and effect
flowchart (SIPOC) map the value of pursuing different processes
[5 empty] | eg. Traveler |  |  | 8: checksheet
Pareto diagram/bar chart - help find critical/most critical issues
Histogram-
[5 empty] | repetitive process=+/- 3 sigma |  |  | 8: Control Chart upper and lower limits (+/- 3-99.73% or 6-99.99% sigma), rule of 7 - out of control
Scatter diagram-correlation
Benchmarking, stat sampling other..
Design of Experiments - Det. What variables will improve quality
Quality management plan
Quality metrics
Quality checklist
Process Improvement plan
+ Force Field analysis - asses pros and cons of the qm plan
HR | planning | plan humna resource management | [5 empty] | 8: 1) behavoural 2) administrative management topics
creating recognition and reward system
[6 empty] | PM |  | 8: improving team members competencies
[6 empty] | PM |  | 8: formally plans team building in advance
[6 empty] | Sponsor |  | 8: gathers support for ht eproject
[6 empty] | Sponsor |  | 8: ensures by-in throughout the organization
[6 empty] | Sponsor |  | 8: gives PM authority
[6 empty] | Sponsor |  | 8: sets priority between projects
[6 empty] | Sponsor |  | 8: supplies risks
[6 empty] | Sponsor |  | 8: sets management report requirements
[6 empty] | Sponsor |  | 8: helps evaluate schedule trade-offs
[6 empty] | Sponsor |  | 8: protects project from outside influences and changes
[6 empty] | Sponsor |  | 8: resolves conflicts beyond PMs control
[6 empty] | Sponsor |  | 8: approves /rejects chagnes or authorizes someone to do so
[6 empty] | Sponsor |  | 8: works with PM to monitor progres
[6 empty] | Project Team |  | 8: id requirements
[6 empty] | Project Team |  | 8: id constraints and assumptions
[6 empty] | Project Team |  | 8: create wbs
[6 empty] | Project Team |  | 8: id schedule dependencies
[6 empty] | Project Team |  | 8: provide estimates
[6 empty] | Project Team |  | 8: participate in the risk management process
[6 empty] | Project Team |  | 8: comply with quality and communication plans
[6 empty] | Project Team |  | 8: help enforce ground rules
[6 empty] | Project Team |  | 8: recommend changes to the project, including corrective actions
[6 empty] | Functional manager |  | 8: provide subject matter expertise
[6 empty] | Functional manager |  | 8: approve final project management plan
[6 empty] | Functional manager |  | 8: assist with problems related to team performace
[6 empty] | Functional manager |  | 8: improve staff utilization
[6 empty] | PM |  | 8: does not have to be a technical expert
determine resources needed
create project job descriptions
understand the team members need for training
send out letters of commendation to team members
address team meber needs
create recognition and award systems
[6 empty] | Portfolio manager |  | 8: Governance at an executive level of project
[6 empty] | Program manager |  | 8: Ensure projects support the strategic goals of the company
EPA-hidden agendas, anyone not wanting the project, colated resources, contract help?, avai. For training.
Responsibility assignment matrix (RAM)
|  |  |  | (Clear division of roles for internal and external) |  |  |  | 8: RACI - responsible, accountable, consult, inform - | activity, team member 1, 2, 3, etc
Resource breakdown structure by People (Dept), matherials, equipment
Staffing managmeent plan, where, when, needs, R&R, compliance, safety
Rewards and recognition
awards prizes/team mbmer of the month
plan milestone parties
Communications | planning | plan communications management
[6 empty] | PM |  | 8: 90% of the time communicating
[6 empty] | (Communications Tool) |  | 8: WBS
EEF-culture and expectations
[6 empty] | PM |  | 8: Ask people what information they need and when?
Analyze how location, culture, sercurity, privacy and language will impact communications
Documents to communciate on a project
project charter
project management plan and documents
impacts to and from other projects
WBS
when resources will be needed
meeting schedule
work assignments
status
new risks
uncertainties
problems
Successes
chagne to project scope and product scope
schedule of planned reviews of the project management plan and when updates are likely to issued
updates to the project manageme plan or product doements
results of change requests
upcoming work
delays
the date of the next milestone completion party
performance reports
lessons learned
issue logs
configuation management issues
what types of e-mails wil be sent to each stakeholder
contact information for all stakeholders
method of updating the communications management plan
escalating issues
communications log
(communications models based on:)
receivers environment, experience, langugage, and culure affect
Rules for meetings
set a time limit, and keep to it
sheducule recurring meeting sin advance
meet with the team reularly, but not too often
Have a purpose for each meeting
Create an agenda with team input
distribute the agend before had s
sticke tht eagenda
let pople know their responsiblities in advance
bring the right people togeter
Chari and lead the meeting with a set of reules
Assign deliverables and time limits for all work assignment tha reuslt from tmeetings
Document and publish meeting minutes
[8 empty] | 8: # of communication channels (N(N-1)/2 | n=prm
Risk | planning | plan risk management |  |  | (see Visio chart) | PM |  | 8: Increase probability of oppurtunities and decrease the probability and impact of treats
Focus on preventing issues - Eliminate treats and increase opportunities decrease estimates for work
Stay in control of the project rather than be controlled by it
OPA-Risk category list (Risk management plan)
EEF-industry studies, risk databases
float, scale, contingency, legal, contract, delays, acceptance, lackof knowledge, performance, sources of risk, risk apetitite
articles written about similar projects and others, charter, lessons learned, stakholder register, risk register
articles similar scope, lessons learned, proc., pred., roles, response.,auth. Level for decisions,risk management
experts;risk appetite, tol, threshold, culture risk; Charter-risks id’d, object, constraints, new, Academic studies,
Project Charter -id risks, inherent, PMP – adequate, Scope Baseline-complexity, scope statement,
Network diagram-path convergence, Estimates – initial, detailed (O), SMP – agressiveness,float,
CMP – cost processes a risk, ComMP-suff. Comm, legal, QMP – metrics, HRM-id deficiencies,
Proc. Doc. - #contracts, level of exp., Stakeholder register - resistance
Risk factors:
Threats, Opportunties, Uncertainty – assumptions made to draw conclusions, Risk to Critial path
from other activities
Risk factors – proability of occurance, range of outcomes (qual), timing, when,
anticipated frequency, level of impact
Stakeholder risk appetite tolerance, threshold, adversity
How will RM be performed, by who (resources) , cost, when, categories, proability, stakeholder tolerances, reporting. Req., audit, communicated
Risk Management Plan (O)
Risk Categories
Type I: External, Internal, Technical, Unforeseeable
Type II: Business, Pure (insurable) Type III: known and unknown risks (contingencies.)
Categories: customer, lack of PM effort, Ladk of PM knowledge, customers customers, suppliers,
resistance to change, cultural differences, schedule, cost, quality, scope, resources, customer
satisfaction (stakeholer staisfaction)
id risks- Overall project exposure (go/no-go) List of risks, potential responses, root causes of risks
Doc. Reviews, Informaiton gathering Techniques (brainstorming-large #,
|  |  |  | Facilitated workshops-prepared, spontaneous |  |  |  | 8: deplphi-anonymous experts, interviewing-most successful, root cause analysis), SWOT,
chekclist analysis (BPA), * Assumptions analysis, diagramming (cause and effect, flowcharts), Experts
Risk Register (O)
[8 empty] | 8: Qualitative Risk Analysis |  |  | x | pm | O
Create a short list (i.e. items that can be controlled)
Scale of Impact: | [7 empty] | 8: Id: 1. Probability of risk, 2. impact ($Amount +/-) = score 3. prioritize high-to-low
10-project failure | [7 empty] | 8: Probability and Impact Matrix (Treats ¦ Oppportunties, Subjective rating)
9- over budget by 40% or project delayed by 40% | [7 empty] | 8: Probability X Impact
8- over budget by 30-40% or project delayed by 30-40% | [7 empty] | 8: Probabilty Scale: Low (1,2), Med (3,4),
7- over budget by 20-30% or project delayed by 20-40% | [7 empty] | 8: Md-High(High), Fact (9-10)
6- over budget by 10-20% or project delayed by 10-20% | [7 empty] | 8: Scale for Impact
5-Slightly over budget | [7 empty] | 8: Risk Data Quality Assessment (analyze precision and allow anonymous contributions)
4-large reduction of time or cost reservers | [7 empty] | 8: Extend of understanding, data avail. About risk, data quality, data reliability and integrity
3-med red of time or cost reserves | [7 empty] | 8: Risk Categorization (by work packages, schedule)
2-small reduction of time or cost reservers | [7 empty] | 8: Risk Urgency Assessment (priority-to move fast on)
1-no real impact | [16 empty] | Risk Register updates (O)
1.Project Ranking
2.Prioritized risks (list)
3.Secondary – additional analysis and response (list #2)
4.Near Term – req. additional analysis
[8 empty] | 8: (review periodically) | 5.Non critical (Watch list)
Perform Quantitative Risk Analysis (For high-prioritized list, Not always required)
Which risk needs a response, determine overall project risk exposure, prob of reaching objectives
(XX% change of completing project within budget of $XX,XXXX), Determine Cost and Schedule
reserves, id risks warranted most attention.
Determining Quantitative Risk Analysis
Methods: interviewing, cost and imte estimaitng, Delphi technique, historical records, expert judgement, …
Sensitivity analysis: Tornado Diagram & ..http://mba.tuck.dartmouth.edu/toolkit/help4.html
Expected Monetary value analysis (EMV=PxI)
Montecarlo Simulation (ater xxxxx times, prabability result would be met or not met
( http://reference.wolfram.com/mathematica/howto/PerformAMonteCarloSimulation.html)
Decision tree – consider future events, calc. EMV, is mutual exclusive (Cost of risk response or not)
Risk Register updates (O)
-prioritized list, contingency time and cost,
realistic completion and confidence, prop.
Of metting objectives, ID risk trends to follow
Plan Risk Responses and assign a responsible owner
Ways to reduce or eliminate threats, make opportunities more likely
Decrease/increase probability or impact of threats/opportunites
Contingency plans if risk happens, fallbackif contingency not effective
Risk response strategies:
[must be timely, appropriate, address more risks, or root causes, involved all]
Threats – Avoid (elim. Cause), Mitigate (reduce), transfer (outsource, delect, allocate)
Opportunites – Expolit (make occure), Enhance (increase chance), Share (outsource)
Transfer and acceptance (low prioirity, low impact)
PMP updates, Project Docs.
Risk register – residual, Cont. Fallb, Owners, 2nd,
triggers, contract, reserves (O)
Procurement | planning | plan procurement management
[5 empty] | 2 days, (O) |  |  | 8: Procurement Management plan | buyer |  | x | pm | blob
|  |  | input | db-table |  |  |  | 7: input-OPA; 8: Procurement documents, NDA< Stndard Contract,Special conditions, T&Cpg 490 (32), LOI |  |  |  |  | table
|  |  | input | db-table |  |  |  | 7: input-EEF |  |  |  |  | table
[5 empty] | 2-14 days, (O) |  |  | 8: Procurement statement of work+meetings, reports actions, communicaitons, acceptance criteria, process of gaining acceptance | buyer |  | x | pm | blob
[8 empty] | 8: Review contract scope meets requirements | x |  | x | pm
Contract change control procedure
[8 empty] | 8: Create RFP< IRB, RFQ | buyer |  | x | buyer
[8 empty] | 8: Identify procurement risks and follow risk management procedure | x |  | x | pm
Select the appropriate contract type
|  | input-OPA | [5 empty] | 7: Conduct procurements; 8: PreQualified Seller list
[6 empty] | PM |  | 8: Provide and understanding of the risks to the subcontractor or supplier
[5 empty] | (Synchornize Objectives) |  |  | 8: Incentives
[5 empty] | Objective: protect relationship |  |  | 8: Contracts
Stakeholder | planning | plan stakeholder management | [5 empty] | 8: Key Objective: SATISFACTION
Communications | executing | manage communiations
ommunications management plan
EEF
OPA
T7T: technology, models, methods, information management system, performance reporting
mitigate communication issues:
noise, distance, impropoer encoding, negative statemetns, hostility, language, culture
[6 empty] | (performance reporting) |  | 8: how th eprjoect is doing?
compared to its baseline
how is it likel to go forward
needs for the project
status, progress, trend, forecasting, variance, Earned Value, lessons learned
HR | executing | acquire project team | [5 empty] | 8: T&T : Pre-assingment, Negotiation, Acquisition, Multi-criteria Decision Analysis and Virutal Teams
[8 empty] | 7: Human Resource management plan | Resource Calenders
project staff assignments | bar: 7 to 9
project management plan updates | bar: 7 to 9
HR | executing | develop project team
[6 empty] | PM |  | 8: Guide, manage, and improve the interactions of team members
[6 empty] | PM |  | 8: incorporate team-building activities
[6 empty] | PM |  | 8: improve trust and choesivenes
[6 empty] | PM |  | 8: WBS Creation is a team-building tool
Team-building
Forming-people brought together a s a team
Storming-disaggrements as people learn to work together
Norming-teams begin to build new relationships
Performing - becomes efficience and works to together
Adjourning - project ends, disbanded
[7 empty] | team Activites | 8: taking classes together, milestone parties, holiday and birthday celebrations, outside of work trips, create WBS, getting veryone invovle some way in the pllaning
Have stakeholders periodically review requirements
[7 empty] | ground rules | 8: honesty, conflict resolution, notifying of difficulty, interruptions, taking over meetings or talking too much
joining a meeting late, doing other things during meetings, chain of command, authorizations, status update format and frequency
co-rdiante/approve chagnes in normal/emergency situations
HR | executing | manage project team
Actively resolve conflicts,Encourage, working with, negotiate, lead, observer, issue log, stying in touch, apprasials, good decisions, influence
[7 empty] | Powers | 8: Formal (Legitimate) - position
Reward - giving rewards
Penalty(Coercive) - ability to penalize
Expert - technical or project management expert
Referent - from another liking you.
Management and Leadership styles
Directling-telling
Facilitating - cordinates input
Coaching - helps others
Supporting - provide assistance
Autocratic-top down
Consultative - bottoms p for influence
Consultative-Autocratic-solicits, but makes decisions
Consensus - group
Delegating - gives authority
Bureaucratic - following procedures
Charismatic - energize and encourage
Democratic or Participative - encourageing
Lasissez-faire - allow to act
Analytical - interiew style communicaiton
[6 empty] | PM | Avoid conflicts | 8: Informing team of :
-Direction
-constraints and objectives
-content of charter
-all key decisions
-changes
Assigning work wihtout amiguity, or overlapping resonsibilities
Making work assignments interesting and challenging
Following good project management and project planning practices
Schedules
Sources of conflict
Project priorities
Resources
Technical opinions
Administrative procedures
Cost
Personality
Conflict resolution techniques
Collaborating - openly discuss differences, incorporate multiple viewpoints
[5 empty] | Searching for solutions |  |  | 8: Compromising - finding mutally agreeable soutions
Withdrawal (Avoidance) - retreat or postpone a decision on a party
Smoothing (Accomodating) - emphasize agreement
Forcing (Directing) - pusing a viewpoint at the expense of another
Expectance theory - belief, efforts lead to rewards, with rewards
Motivatinio theory
Mcgregors Theory X and Y sad and happy
|  | Social=belonging |  | Safety need=salary |  |  |  | 8: Maslows Hierachy of needs
|  | Esteem=challenging | [5 empty] | 8: David McClellands Theory of Needs
Achivement - need challenging projects, reachable
Affiliation - seek coorporating, approval
Power - effective, manage others, organize and influence
Herberg's
Hygene factors (motivators): working conditions, salary, personal life, relationships, security, status\
Motivation agents (work itself): responsibliity, self-actualization, professional growth, recognition
Project docs, pmp updates
EEF, OPA updates
change requests
HR Theories
[9 empty] | Power | Motivational Theory |  | Team Dvpmt | Stage | Conflict | Resolution | Style | Leadership Style
[8 empty] | 8: Legitimate; 9: Maslow Hierarchy of; 11: Forming; 4: Confronting | Autocratic &
Directing
[8 empty] | 8: Penalty; 9: McGregor X & Y; 11: Storming; 4: Compromise | Consensus & Participating
[9 empty] | Referent | Herzberg Hygiene |  | Norming |  | Smoothing
[9 empty] | Expert | Expectancy |  | Performing |  | Forcing
[9 empty] | Reward | McLelland's Achievement |  | Adjourning |  | Withdrawal Collaborating
(How Google manages…)
Procuurements | executing | consduct procurements
[6 empty] | PM |  | 8: Answer seller's questions about the procurement documents
[6 empty] | Procurement manager |  | 8: Negotiation Process
Advertising, Issue RFP, IRBm RFQ
Hold Bidder conferences
Select bidder based on Source Selection Criteria pg 488 R
Review and screen proposals, presentations
Resource calenders
|  |  |  | intranet |  |  |  | 8: Create and review contracts-puposwe pg 499 | buyer |  | X | buyer
[8 empty] | 8: Negotiate contracts | buyer | x | x | buyer
Manage relationship between buyer and seller
Manage contract performance
[8 empty] | 8: Initiate change to the contract | buyer |  | x | pm
contract management
Integration | executing | direct and manage project work
Quality | executing | perform quality assurance
Quality audits
process analysis-measure
Affinity - organize and group results of a root cause analysis
Tree diagrams - organize and map out relationships
Matrix-two or more sets of items
prioritization matrix - decision analysis about components of process
[5 empty] | Output: Metrics | [11 empty] | Measurements
validated changes
work performance information
verfied deliverables
Communicaitons | M&C | control communications
formal data collection and evaluation techniques to moniotr and control, and measure effectiveness and efficiency
sender-receiver model (remove barriers to communication)
Integration | M&C | monitor and control project work
monitor the implementation of approved changes
Integration | M&C | perform integrated change control
Risk | M&C | control risks | [5 empty] | 8: Implement plans, workarounds, track id ricks, monitor residual risks, (meetings id new risks),
[9 empty] | T&T | risks and reasessments, risk audits, variance and trends analysis, reserve, analysis meetings
close risks, eval. Risk process effectiveness (variance/trend analysis, eval. assumptios,
|  |  | Risk tolerance: aversion, seeker, neutral risk taker |  |  |  |  | 8: reassessments (team), risk audits, cost/sch reserve analysis)
Risk Register updates
(outcomes, results, id, new , what happened,
lessons learned),
change req. prev/correc action (O)
Risk | mon & con |  | @ status meetings | dashboard |  |  |  | 8: RMP-(within stakholder risk appetite, tolerance, thresholds); 4: prob of occur., range of outcomes, timing, anticipated frequ, level of impact
| mon & con |  | daily | log |  |  |  | 7: (risk register); 8: risk assement, track id ricks, monitor residual risks, (meetings id new risks), close risks, variance/trend analysis (threshold)
| mon & con |  | bi-weely/monthly | log |  |  |  | 7: date-trigger-action; 8: Cost/sch reserve analysis, eval. assumptios, reassessments (team)
| mon & con |  | periodic | log |  |  |  | 7: date-trigger-action; 8: audit of risk management plan
| mon & con |  | Need-Ad hoc | risk register |  |  |  | 8: Implement plans, workarounds,, eval. Risk process effectiveness ()
| mon & con |  | changes | sponsor, risk reg. |  |  |  | 7: changes; 8: update risk regsiter
Scope | M&C | validate scope | [5 empty] | 8: formalize acceptance, before testing
Work Performance info., change requests, Accepted deliverables, project document updates (O)
Completed Deliverables -> QC - > Meet with Customer
project mp, req. do., req. tracability matrix, verifed deliver., work performance data, change requests
Scope | M&C | control scope
- Measuring and assessing work performance data against scope baseline
- Managing scope baseline changes
requirements documentation
sp
measure work performance and analyze variances
procurements | M&C | control procurements | [5 empty] | 8: T&T:
change control system, performance review, inspections, audit, perf. Reporting, payments sys
claims admin, records management system
updates
change requests
work performance information
Record every phonecall with seller
Hold performance review meetings
Report on Performance
Monitor cost, schedule, and technical performance
Control quality
review claims
Send copies of changes to all parties
Accept verified deliverables
Validate scope being performed
Validate changes completed
Perform Inspections and audits
Identify new risks
Restimate risks, monitor and control risks
Manage claims adminsitration process
Control records management
Schedule | M&C | control schedule
Looking for things causing the changes and influence, review performance, reestimate, performance reviews, trend analysis, adjust to deal with delays, adjust reports to manage projects, follow change control process.
Agile
- lessons learned to implement process improvements, reprioritize backlogs, id and mange change
reestmate work part-way during remaining of project
conduct performance reviews
perform trend analysis
adjust to deal with delays
use reporting to help capture and manage project
Agile-holding lessons learned for process improv., reprior backlog, id and manage changes
[8 empty] | 8: review work performance data | Work performance informaiton
schedule forecasts
change requests
PMP updates
PD updates to schedule, risk register
Cost | M&C | control costs | [5 empty] | 7: Funding requirements
Work performance data
Researve analysis - if reserves are still necessary and if new is required
Reporting/Earned Value
[8 empty] | 8: measure, and determine need to request changes | change request
[9 empty] | Cost variance (CV) |  |  | EV- | AC
[9 empty] | Schedule variance (SV) |  |  | EV- | PV
[9 empty] | CPI |  |  | EV/ | AC
[9 empty] | SPI |  |  | EV/ | PV
|  | Earned value - estimated value of work completed | [5 empty] | 8: EAC; 11: AC+Bottom-up ETC |  | orrig. Est flawed
|  | BAC- how much budgeted for todal project | [5 empty] | 11: BAC/CPI |  | same rate of spending
[8 empty] | 11: AC+(BAC-EV) |  | var atypical of future
[8 empty] | 11: AC+(BAC-EV)/CPIXSPI |  | var typical of future
[7 empty] | TCPI inverse of CPI | 8: To complete performance Index; 11: BAC-EV/BAC-AC
[9 empty] | ETC |  |  | EAC-AC
[9 empty] | VAC |  |  | BAC-EAC
Quality | M&C | control quality | bar: 8
deliverables
work performance data
apporved change reequests
project documents
quality metrics, checklists
eef, opa, doc updates | bar: 8
QC measurements | bar: 8
validated changes | bar: 8
validated delvierables | bar: 8
work performnace information | bar: 8
change requests | bar: 8
Procurements | Closing | close procurements
verify deliverables are accepted, and finanlized
fainlize any open claims
audit contract
final contract performance reporting
pay withheld retainage
lessons learned
close file-changes, submittals, performance reports, financial informaiton, inspection results, lessons learned
Issue formal acceptance
Integration | Closing | close project or phase
Professional and Social Repsonsibility | bar: 8
Responsibility
must obtain the responsibility necessary to manage the project
At minimum have a charter and WBS
make interests on the best interest of the company, than own inerest
Only accept qualified assignments
protect proprietary information
report unethical behavour and violations
Respect |  | maintain an attitude of mutal coorporation, respect cultural differences, good faith negotiations, be direct with conflict dealings, not use own's influence for power and influence
Fairness
forcing resources to make the deadline by working overtime is not an ethical solution
act impartially without bribery
disclose conflicts of interest, do not discriminate
Honesty
unethical to provide an inaccurate schedule
understand the truth, be truthful
PMIs Code of Ethics and Professional Conduct
Daily
check customer's RVI (requirements volatility)
document rights management software for sharing the project charter
set access rights to documents
customer signs the requirements document
check organization and resource calenders
procurement contract clause not to include ip from others
As new team members added, inofmratl team building
Review weather and have a contingency plan
regular id and assesment of team skills
periodically review the business case
request client feedback after key reviews
review project risks at all team meetings
conduct procurement audits
audit cost submittals on a cost-reimbursable contract
celebrate-showcase developments, challenges, lessons learned
request letter accepting delivery
before closing-review project management plan
@closing review scope baseline
Complexity
|  | Charter |  |  | Six signatures on the Charter |  |  | 8: complex configuration management (depts.)
Issues
|  | PM |  |  | take over from PM |  |  | 8: assess what works and replicate
|  | complex problems | [5 empty] | 8: written communications
|  | scope |  |  | team member claims no impact, due to unauthorized change
|  | scope |  |  | New distinct scope |  |  | 8: develop charter
|  | scope |  |  | Adding change
|  | schedule |  |  | schedule too long,
|  | budget |  |  | run out of money |  |  | 8: Close project or phase
|  | procurement |  |  | overcharges |  |  | 8: Do not halt payments, will be a breach of contract
|  | procurement |  |  | not performiang workin contract |  |  | 8: issue default letter
|  | resources |  |  | resources promised not provided |  |  | 8: Explain impact
|  | resources |  |  | primary customer requests change |  |  | 8: prepare change request
|  | resources |  |  | team member performance |  |  | 8: informal non-verbal
|  | resources |  |  | unfair labor standards |  |  | 8: don't proceed
|  | resources |  |  | cultural differences |  |  | 8: hold-team building with everyone providing unique informaiton on their culture
|  | rescources |  |  | discover issue |  |  | 8: confront and validate first, and report if necessary
|  | communications |  |  | report errors |  |  | 8: cancel and reschedule meeting
Project plans and documents | [22 empty] | qualifications
| 0 | project management plan (18)
| 1 | Activitie attributes
| 2 | activit cost estimatesactivity duration estimaties
| 3 | activity list
| 4 | activity resource reqirements
| 5 | agreements
| 6 | basis of estimates
| 7 | change log
| 8 | change requrests
| 9 | forecasts - cost
| 10 | forecast - schedule
| 11 | issue log
| 12 | mileston list
| 13 | procurement documents
| 14 | procurement statement of work
| 15 | project calendars
| 16 | project charter
| 17 | project funding requirements
| 18 | project schedule
| 19 | project schedule
| 20 | project schedule network diagrams
| 21 | project staffing assignments
| 22 | project statement of work
| 23 | quality checklists
| 24 | quality control measurements
| 25 | quality metrics
| 26 | requirements documentation
| 27 | requirements traceability matrix
| 28 | resource breakdown structure
| 29 | resource calenders
| 30 | risk register
| 31 | schedule proposlas
| 32 | source selection criteria
| 33 | stakholder register
| 34 | team performance assessments
| 35 | work performance data
| 36 | work performance information
| 37 | work performance reports
| 38 | evironmental
| Risk | asset development | [5 empty] | 8: supply chain analysis - before and after (Zurich and Aon risk management)
|  | asset development | [5 empty] | 8: submittal review and schedule
|  | asset development | [5 empty] | 8: physical inspection and on-site tests
|  | asset development | [5 empty] | 8: bonded warehouse
|  | asset development | [5 empty] | 8: product allocation
|  | asset development | [5 empty] | 8: price contracts
|  | asset development | [5 empty] | 8: capacity; 9: fallback
|  | asset development | [5 empty] | 8: end-of-life
| 39 | organization process assets
|  | software development | [5 empty] | 8: SWBOK
|  | software development | [5 empty] | 8: technology cost /benefit map and tradeoff
|  | software development | [5 empty] | 8: Secuirty Development lifecycle
|  | software development | [5 empty] | 8: How google tests, book
|  | software development | [5 empty] | 8: Agile SCRUM
|  | software development | [5 empty] | 8: requirements, code control, config, change, build autom, cont. integra.,unit test release engr.
|  | software development | [5 empty] | 8: design practices
|  | software development | [5 empty] | 8: design consideration
|  | software development | [5 empty] | 8: Architectural patterns and techniques, cost benefit (SEI Cost Benefit Analysis Method (CBAM), Architecture Tradeoff Analysis Method (ATAM))
|  | software development | [5 empty] | 8: Evaluating Software Architectures: Methods and Case Studies
|  | software development | [5 empty] | 8: Integrating Software-Architecture-Centric Methods into Extreme Programming (XP)
|  | software development | [5 empty] | 8: Integrating the Architecture Tradeoff Analysis Method (ATAM) with the Cost Benefit Analysis Method (CBAM)
|  | software development | [5 empty] | 8: Making Architecture Design Decisions: An Economic Approach
|  | software development | [5 empty] | 8: Quantifying the Value of Architecture Design Decisions: Lessons from the Field
|  | software development | [5 empty] | 8: NCEES engineering process
|  | software development | [5 empty] | 8: UML
|  | software development | [5 empty] | 8: libraries
|  | software development | [5 empty] | 8: programming practices